## Read Me
Protein Bar Thao Dien — Budget & Launch Workbook
Prepared 8 Aug 2026 · All amounts VND unless marked USD · Structure: Vietnamese-owned LLC (recommended path)
LEGEND
Blue text |  | Hardcoded input / assumption — you can edit these
Black text |  | Formula — do not overwrite
Green text |  | Link to another sheet
Yellow fill |  | Key levers to review with partners, or cells for the intern to fill in
GLOBAL INPUTS
FX rate (VND per USD) | 26000 | Aug 2026 approx. interbank rate — update monthly
Floor area (m2) | 80 | Target premises size, ground floor
Scenario in use for cash plan | Standard | Lean = takeover (sang quán) · Standard = new fit-out, secondary street · Premium = prime street
TABS
1. Setup Budget |  | One-time investment, 3 scenarios (Lean / Standard / Premium)
2. Monthly P&L |  | Operating model, 3 revenue cases + break-even
3. Cash Plan |  | Month-by-month cash needed from now to opening + reserve
4. Milestones |  | 16-week plan with weekly progress markers and hard gates — intern updates Status weekly
5. Suppliers |  | 12-supplier long-list + trial scorecard (goal: trial 5–10, pick 1 main + 2 backup)
KEY SOURCES
Rents |  | mogi.vn / batdongsan.com.vn Thao Dien listings Aug 2026; CBRE Q4-2025 HCMC Figures
Licensing costs |  | Decree 168/2025/ND-CP (registration); Circular 67/2021/TT-BTC (food safety fee); HCMC agency quotes 12–15M VND
Wages |  | Decree 293/2025/ND-CP: Region I minimum 5.31M VND/mo from 1 Jan 2026; market barista wage 7–10M gross
Prices/competitors |  | Thao Dien field data: specialty coffee 50–85k, smoothies 50–90k, poke 190k, Starbucks latte 85–105k

## Setup Budget
One-Time Setup Budget (VND)
Lean = take over existing fitted cafe (sang quán) on side/secondary street · Standard = new fit-out, secondary street (Quoc Huong tier) · Premium = prime (Xuan Thuy / Thao Dien St)
Item | Lean | Standard | Premium | USD (Std) | Notes / source
LICENSING & LEGAL
Company registration — VN LLC via agency (ERC, seal, tax setup) | 12000000 | 12000000 | 12000000 |  | Gov fees <1M; agency 8–15M. ERC in 3–6 working days. Decree 168/2025
Food safety certificate (state fee + agency service) | 13000000 | 13000000 | 13000000 |  | State fee 700k (Circ. 67/2021); HCMC agency full service 12–15M; 15–20 working days + inspection; valid 3 yrs
Product self-declarations (tự công bố) — only for own-label/imported SKUs | 0 | 8000000 | 20000000 |  | Resale SKUs use the SUPPLIER's declaration (collect copies — free). ~4M/SKU incl. lab test when you self-declare
PCCC file + fire equipment (extinguishers, exit signage, plan) | 8000000 | 15000000 | 25000000 |  | Decree 105/2025 — small ground-floor cafe = self-compliance file; verify category with ward police
E-invoice + digital signature + cash-register software setup | 5000000 | 5000000 | 5000000 |  | Decree 70/2025: F&B company must use tax-connected cash register e-invoices
Staff health checks + food-safety training records | 3000000 | 3000000 | 4000000 |  | 100–300k/person at district hospital; owner self-certifies training (Decree 155/2018)
Lease legal review + notarization | 3000000 | 3000000 | 3000000 |  | Notarize lease >6 months; check sổ hồng + commercial use
Trademark filing (brand name + logo, NOIP) | 4000000 | 4000000 | 4000000 |  | File in Week 2 — takes 18–24 months to grant, needed before OEM phase
PREMISES ENTRY
Monthly rent (assumption, drives deposit) | 25000000 | 35000000 | 55000000 |  | Field data Aug 2026: side street 20–35M; Quoc Huong tier 30–55M; Xuan Thuy prime 50–90M for 60–100m2
Deposit (3 months) + 1 month advance = 4x rent |  |  |  |  | Standard HCMC F&B terms; negotiate landlord-early-termination penalty = 2x deposit
Sang quán takeover fee (Lean only) | 200000000 | 0 | 0 |  | Fitted 50–100m2 cafes ask 100–400M; includes fit-out + sometimes grease trap/licence groundwork
FIT-OUT & EQUIPMENT
Fit-out / renovation (counter, walk-through window, seating 15–17) | 150000000 | 560000000 | 900000000 |  | Standard = ~7M VND/m2 x 80m2 mid-grade; Lean = refresh of taken-over space; incl. furniture
Blenders x2 commercial (Blendtec/Vitamix class) | 40000000 | 40000000 | 50000000 |  | ~20M each; buy 1 spare later
Refrigeration: display fridge, under-counter, freezer | 55000000 | 60000000 | 80000000 |  | RTD display case is the shop window — don't cheap out
Espresso machine + grinder (proffee menu line) | 80000000 | 110000000 | 170000000 |  | 2-group mid-range; protein coffee is a key local-friendly bridge product
Kitchen: combi/air fryers, induction, prep tables, grease trap | 60000000 | 80000000 | 120000000 |  | Light-cook protein food; grease trap required for food safety cert
POS hardware + tablets + wifi/network (coworking-grade) | 18000000 | 22000000 | 28000000 |  | Dual-band wifi + outlets at every seat is part of the product
Smallwares, uniforms, first-aid, misc | 20000000 | 25000000 | 30000000
BRAND & LAUNCH
Signage + facade + menu boards | 25000000 | 40000000 | 60000000 |  | Ordinary shop sign needs no ad permit (size/content rules apply)
Brand identity, packaging design, photography | 15000000 | 20000000 | 30000000 |  | AI-assisted in-house; budget covers printing + pro photos
Website + app + booking/loyalty MVP | 5000000 | 8000000 | 12000000 |  | Built in-house with AI by Klaus + software intern; cost = domain, hosting, tools
Initial inventory (RTD stock, powders, fresh, packaging) | 60000000 | 80000000 | 100000000 |  | Covers ~3–4 weeks at Base volume
Pre-opening payroll (1 month training, 5 staff) | 45000000 | 55000000 | 65000000 |  | See Monthly P&L staff build-up
Pre-opening + launch marketing (soft open, run clubs, gym partnerships, FB/IG) | 40000000 | 60000000 | 90000000 |  | Incl. free-shake vouchers, KOL seeding, opening event
Subtotal
Contingency (10%)
Working-capital reserve (3 months fixed opex, from Monthly P&L)
TOTAL CASH REQUIRED |  |  |  |  | Lean/Standard/Premium totals in USD ≈ =C/FX etc. — see Cash Plan for timing

## Monthly P&L
Monthly Operating Model (VND)
Premises assumption: Standard scenario (secondary street, rent from Setup Budget). Edit blue cells.
Driver | Conservative | Base | Strong | Notes
Transactions / day | 75 | 130 | 180 | Walk-in + takeaway + delivery orders. Break-even ≈ row 31
Average ticket (VND) | 80000 | 85000 | 90000 | Shakes 65–95k, proffee 55–75k, bowls 95–165k, keep 1–2 items ≤49k for locals
Trading days / month | 30 | 30 | 30
COGS % of revenue | 36% | 34% | 32% | Resale RTD ~65–75% COGS on its line; in-house blends ~25–40% — mix shifts this
Delivery share of orders | 20% | 25% | 30% | GrabFood first (50% HCMC share), then ShopeeFood
Delivery platform commission | 25% | 25% | 25% | Price delivery menu +15–20% to offset
REVENUE & VARIABLE
Revenue
COGS
Delivery commissions
Gross profit
Gross margin %
FIXED COSTS (same all scenarios)
Rent (Standard scenario) |  |  |  | Escalation 5–10%/yr typical — model +8% in year 2
Staff: 5 FTE avg 9M gross + 21.5% employer SI |  |  |  | 2 baristas, 2 counter/kitchen, 1 shift supervisor. Region I min wage 5.31M (Decree 293/2025)
Utilities (electricity commercial rate, water, internet) | 15000000 |  |  | AC + fridges heavy; check 3-phase supply
Marketing (ongoing) | 15000000 |  |  | FB groups, run-club sponsorship, gym partnerships, content
Accounting service + bank + admin | 4000000 |  |  | VN LLC full books: 2–5M/mo outsourced
Music royalties (VCPMC), pest control, repairs, misc | 6000000
Total fixed costs
EBITDA (pre-tax operating profit)
EBITDA margin %
Tax note | VAT 8–10% on sales (in prices above); CIT 20% on profit (15–17% small-firm preferential rates — ask accountant)
Break-even transactions / day |  |  |  | Must beat this by month 4–6 of trading or renegotiate rent / cut hours
Payback on Standard setup (months, at this EBITDA)

## Cash Plan
Pre-Opening Cash Plan — Standard scenario (VND)
Aug = Month 0 (setup start) … Dec = opening month. Timing in % of each budget line.
Outflow | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Notes
Licensing & legal (all lines) |  |  |  | 0 | 0 | Company reg + food safety service start immediately
Lease deposit + advance | 0 |  | 0 | 0 | 0 | Target lease signing mid-Sep (Gate 1)
Fit-out | 0 |  |  |  | 0 | 30% down payment on design approval, 50% mid-build, 20% completion
Equipment (all lines) | 0 |  |  |  | 0 | Order fridges/espresso early — 2–6 week lead times
Brand, signage, web/app |  |  |  |  | 0
Initial inventory | 0 | 0 |  |  |  | Samples in Sep–Oct are small; main stock order 2 wks pre-open
Pre-opening payroll | 0 | 0 |  |  |  | Supervisor hired Oct; full team Nov
Pre-opening marketing | 0
Contingency
Monthly outflow
Cumulative cash out
Working-capital reserve to hold at opening | [5 empty] | 3 months of fixed opex — do NOT spend this on fit-out overruns
TOTAL FUNDS TO COMMIT

## Milestones
16-Week Launch Plan — hard deadline: opening by 8 Dec 2026 (4 months)
Intern updates the Status column every Friday: On track / At risk / Done / Blocked. A missed GATE week = escalate to Klaus same day.
Wk | Dates | Phase | Business intern — key tasks | Klaus / partners / software intern | Progress marker (measurable, checked Friday) | Gate | Status
1 | 10 Aug–16 Aug | Setup | Confirm VN LLC shareholding with local partners; brief agency; gather partner IDs; visit An Khanh Ward one-stop office to confirm post-merger procedures; start supplier sample requests (all 12 on Suppliers tab) | Klaus: agree equity/roles in written founders' agreement; choose company + brand name; open shared drive/Notion | Founders' agreement signed · agency engaged · 12 supplier contacts logged |  | In progress
2 | 17 Aug–23 Aug | Setup | File ERC (LLC registration) via agency; collect landlord long-list ≥15 properties (mogi/batdongsan/walking Xuan Thuy–Quoc Huong–side streets); request supplier price lists + tự công bố copies | Klaus: file trademark; draft brand identity v1 with AI; software intern: domain + website skeleton | ERC filed · ≥15 properties logged with rent/size/photos · ≥6 price lists in
3 | 24 Aug–30 Aug | Property hunt | Visit ≥8 properties; check flood marks, sổ hồng, 3-phase power, grease trap, signage rights (checklist in plan doc); first supplier tasting session (score ≥5 SKUs) | Klaus: join 2–3 visits; menu v1 with target COGS per item | ERC issued · shortlist of 3–5 properties · ≥5 SKUs scored
4 | 31 Aug–06 Sep | Property hunt | Negotiate LOI on top 2 properties (ask: 3+2yr term or 2+2, 1 month fit-out rent-free, landlord-termination penalty, sale-survival clause); verify address eligible for business registration; 2nd tasting round | Klaus: decide property with partners; agree max rent; review lease with lawyer | 2 LOIs negotiated · lease draft reviewed · supplier scorecard ≥8 SKUs
5 | 07 Sep–13 Sep | Commit | SIGN LEASE + notarize; measure site; brief fit-out contractor (3 quotes); apply e-invoice/digital signature; open company bank account | Klaus: release deposit; approve fit-out budget cap; loyalty app spec frozen | Lease signed & notarized · 3 fit-out quotes in | GATE 1
6 | 14 Sep–20 Sep | Build | Fit-out design approved incl. one-way kitchen flow (food-safety layout!), walk-through counter, grease trap; PCCC self-compliance check with ward police; order long-lead equipment (espresso, fridges) | Software intern: website live w/ menu + maps; Klaus: confirm 2–3 anchor supplier deals (main + backups) | Design signed off · equipment ordered · PCCC category confirmed in writing
7 | 21 Sep–27 Sep | Build | Fit-out construction starts; staff health checks + food-safety training file; draft food safety cert dossier; hire shift supervisor (refer from partners' network) | Klaus: pricing final (entry item ≤49k); GrabFood/ShopeeFood merchant applications | Construction started · supervisor hired · dossier 80% ready
8 | 28 Sep–04 Oct | Build | Supervise fit-out weekly; recruit 4 remaining staff; collect ALL resale SKUs' tự công bố copies into compliance binder; finalize main supplier + 2 backups with signed price agreements | Klaus: brand photography; app beta to 20 testers | Staff hired · compliance binder complete · supplier agreements signed
9 | 05 Oct–11 Oct | Build | Fit-out mid-point check vs quote; utilities connected (3-phase, water); wifi + POS installed; staff training week 1 (drinks, food, POS, hygiene) | Klaus: opening campaign plan (run clubs, 3 gym partnerships, FB groups seeding) | Build ≥70% done · POS live in test mode
10 | 12 Oct–18 Oct | Certify | SUBMIT food safety certificate application (needs finished kitchen); equipment installed & tested; menu lock; e-invoice live test | Klaus: sign 3 gym/run-club partnership deals (member discount + PT codes) | Food safety application submitted · kitchen operational | GATE 2
11 | 19 Oct–25 Oct | Certify | Prepare for inspection (mock audit with checklist); staff training week 2; inventory soft order; GrabFood/ShopeeFood menus uploaded | Software intern: loyalty/stamp feature live; Klaus: KOL seeding shortlist 10 fitness influencers | Mock audit pass · delivery menus approved
12 | 26 Oct–01 Nov | Soft open | Food safety INSPECTION expected; soft opening for friends/partners/run clubs (limited menu, feedback forms); fix ops daily | Klaus: host 2 community events (post-run shakes); measure ticket times | Inspection passed or gaps fixed within 48h · 300+ soft-open customers | GATE 3
13 | 02 Nov–08 Nov | Soft open | Food safety certificate issued; full menu on; delivery channels ON; iterate on top-10 feedback items; stock levels tuned | Klaus: publish opening date; paid FB/IG ads start; press/expat-media outreach (Thao Dien app/guide listings) | Certificate in hand · delivery live · repeat-customer rate tracked
14 | 09 Nov–15 Nov | Launch | GRAND OPENING weekend (aim Sat 5 Dec); opening promos (BOGO shakes, gym-partner discounts); collect reviews (Google Maps ≥30) | All hands: event with run clubs + gyms; influencer posts go live | Opening executed · ≥150 tx/day on peak days · ≥30 reviews ≥4.5★ | GATE 4
15 | 16 Nov–22 Nov | Stabilize | Daily sales/COGS tracking vs P&L tab; staff roster tuning; supplier reorder rhythm; weekly Friday report to Klaus (sales, COGS%, top items, complaints) | Klaus: review scenario vs actuals; start OEM conversations (Wana/Interfresh) with 3-month sales data target | Week avg ≥ break-even tx/day − 20% · COGS within 3pts of plan
16 | 23 Nov–29 Nov | Stabilize | Month-1 close with accountant; VAT/e-invoice reconciliation; customer survey n≥100; university outreach for food-science interns (HCMUT, HUIT, Nong Lam) for OEM phase | Klaus: decide OEM timeline based on velocity; lock Q1 2027 marketing calendar | Month-1 P&L vs budget reviewed · OEM shortlist contacted
Slack: plan lands opening ~5 Dec, 3 days before the 8 Dec hard deadline. If Gate 1 (lease) slips past week 6, pull the sang quán (takeover) option to recover 3–4 weeks of fit-out.

## Task Breakdown
Detailed Task Breakdown (WBS) — every task and subtask, W1–W16 + recurring
Status values: Not started / In progress / Done / At risk / Blocked / N-A. Update every Friday. Gate weeks shaded orange. 'Dep' = must finish before this task starts.
Done: |  | of |  | tasks · Blocked:
ID | Wk | Due (Fri) | Phase | Workstream | Task / subtask (as detailed as it gets) | Owner | Dep | Status | Notes / verification
WEEK 1 · Setup · Friday marker due 14 Aug
1.1 | 1 | 14 Aug | Setup | Legal | Founders' meeting: agree equity %, capital contributions and payment schedule, roles, profit split, exit/buy-out terms, dispute resolution | Klaus+partners |  | Not started | Decision list first, lawyer papers it
1.2 | 1 | 14 Aug | Setup | Legal | Founders' agreement: include IP assignment — brand, recipes, app code all owned by the LLC, not individuals | Klaus+partners | 1.1 | Not started | Prevents the classic co-founder disaster
1.3 | 1 | 14 Aug | Setup | Legal | Engage Vietnamese business lawyer: founders' agreement + Klaus's consultancy/service agreement for his economics | Klaus | 1.1 | Not started | Few million VND; NOT optional
1.4 | 1 | 14 Aug | Setup | Legal | Choose company name — check availability on dangkykinhdoanh.gov.vn national registry | Klaus+partners |  | Not started | Agency can check in minutes
1.5 | 1 | 14 Aug | Setup | Legal | Choose brand name — check NOIP trademark register + Facebook/Instagram handle + .vn/.com domain all available | Klaus |  | Not started | Do all 4 checks BEFORE falling in love with a name
1.6 | 1 | 14 Aug | Setup | Legal | Get 3 registration-agency quotes (scope: ERC + seal + tax + bank support + food safety cert service); select one | Intern |  | Not started | Budget ~12M VND all-in
1.7 | 1 | 14 Aug | Setup | Legal | Collect partner documents: CCCD/ID copies, residential addresses, phone numbers for filing | Intern | 1.6 | Not started
1.8 | 1 | 14 Aug | Setup | Legal | Visit An Khanh Ward one-stop office: confirm post-merger procedures, forms, queue reality; log officer name + date in Notes | Intern |  | Not started | Field truth #1 — offices reorganised Jul 2025
1.9 | 1 | 14 Aug | Setup | Ops | Set up shared tracker (this workbook on Drive) + team Zalo group + weekly Friday report template | Intern |  | Not started
1.10 | 1 | 14 Aug | Setup | Suppliers | Send bilingual intro + sample/price-list request to all 12 suppliers on Suppliers tab (Zalo/WhatsApp/email per contact column) | Intern |  | Not started | AI-draft the message, intern reviews before sending
1.11 | 1 | 14 Aug | Setup | Suppliers | Log the 2 existing supplier conversations into the Suppliers scorecard with current quoted prices | Intern |  | Not started
1.12 | 1 | 14 Aug | Setup | Property | Set alerts on mogi.vn, batdongsan.com.vn, nhatot, dotproperty; join FB groups (Thao Dien residents 32k, sang quán cafe groups) | Intern |  | Not started
WEEK 2 · Setup · Friday marker due 21 Aug
2.1 | 2 | 21 Aug | Setup | Legal | File ERC via agency — business lines 5610, 5630 (cafe), 4722/4711 (retail packaged drinks), 4633 (wholesale, for OEM later) | Intern | 1.6,1.7 | Not started | 3–6 working days
2.2 | 2 | 21 Aug | Setup | Legal | File trademark application (word mark + logo) at NOIP via agent | Klaus | 1.5 | Not started | 18–24 months to grant — file NOW
2.3 | 2 | 21 Aug | Setup | Property | Build long-list ≥15 properties: street, m2, asking rent, frontage width, floor height vs street, photos — into a comparison sheet | Intern | 1.12 | Not started
2.4 | 2 | 21 Aug | Setup | Property | Walk Xuân Thủy, Quốc Hương, Nguyễn Ư Dĩ, Thái Ly, Trần Ngọc Diện, streets 41/64 for banner-only listings; photograph + call | Intern |  | Not started | Many Thao Dien landlords never list online
2.5 | 2 | 21 Aug | Setup | Property | Screen sang quán (takeover) listings on sangquancafe.com + muaban.net; log any fitted 50–100m2 cafe under 300M VND | Intern |  | Not started | This is the Gate-1 fallback — keep it warm
2.6 | 2 | 21 Aug | Setup | Suppliers | Chase all suppliers; log received price lists; request tự công bố copy for every SKU offered | Intern | 1.10 | Not started | No declaration copy = SKU is dead to us
2.7 | 2 | 21 Aug | Setup | Tech | Register domain + hosting; website skeleton: menu, location, story, bilingual EN/VN placeholders | Software intern | 1.5 | Not started
2.8 | 2 | 21 Aug | Setup | Brand | Brand identity v1 with AI: logo options, colors, tone, cup/packaging mockups — pick direction with partners | Klaus | 1.5 | Not started
2.9 | 2 | 21 Aug | Setup | Menu | Menu v0: draft list — protein shakes (25g+), proffee line, protein iced tea, 3–4 bowls/wraps, grab-and-go fridge SKUs | Klaus |  | Not started
WEEK 3 · Property hunt · Friday marker due 28 Aug
3.1 | 3 | 28 Aug | Property hunt | Property | Book and complete ≥8 property visits from long-list | Intern | 2.3 | Not started
3.2 | 3 | 28 Aug | Property hunt | Property | At each visit run red-flag checklist: sổ hồng photo, owner ID match, commercial use OK, 3-phase power, water/drainage, grease-trap space, signage rights, motorbike parking | Intern | 3.1 | Not started | Checklist is section 4.3 of master plan doc
3.3 | 3 | 28 Aug | Property hunt | Property | Flood check: revisit top candidates during/after heavy rain; photograph wall watermarks; check floor height vs street | Intern | 3.1 | Not started | Thảo Điền st, Quốc Hương, Ng. Văn Hưởng flood sections are disqualifying
3.4 | 3 | 28 Aug | Property hunt | Property | Confirm each shortlist address is registrable for business (ask agency or ward office) | Intern | 3.1 | Not started | Apartments = NO; house/shophouse with owner consent = yes
3.5 | 3 | 28 Aug | Property hunt | Legal | Collect ERC + company seal; register tax; confirm e-invoice provider options with agency | Intern | 2.1 | Not started
3.6 | 3 | 28 Aug | Property hunt | Suppliers | Tasting session #1: ≥5 SKUs, blind format, 5+ tasters, use scorecard (taste, protein g, VND/g protein) | Intern+Klaus | 2.6 | Not started
3.7 | 3 | 28 Aug | Property hunt | Menu | Menu v1 with target COGS per item — priced against the P&L COGS assumption (34%) | Klaus | 2.9,3.6 | Not started
3.8 | 3 | 28 Aug | Property hunt | Property | Produce shortlist of 3–5 with weighted comparison (rent, flood, frontage, gym-catchment distance, legal cleanliness) | Intern | 3.2,3.3 | Not started
WEEK 4 · Property hunt · Friday marker due 04 Sep
4.1 | 4 | 04 Sep | Property hunt | Property | Draft LOI terms: rent + cap on escalation (5–8%/yr), term 3+2 yrs, deposit 3 mo, 1–2 mo rent-free fit-out, landlord early-termination penalty 2× deposit, lease-survives-sale clause, renovation/signage/grease-trap/exhaust consent | Intern+lawyer | 3.8 | Not started
4.2 | 4 | 04 Sep | Property hunt | Property | Negotiate with top-2 landlords — bring a Vietnamese partner to every negotiation | Intern+partner | 4.1 | Not started | Local face moves price 5–15%
4.3 | 4 | 04 Sep | Property hunt | Property | Clarify landlord rental tax (~10%): who bears it — 'chưa bao gồm thuế' quotes must be repriced | Intern | 4.2 | Not started
4.4 | 4 | 04 Sep | Property hunt | Legal | Lawyer reviews chosen lease draft; verify sổ hồng original + planning/road-widening check | Lawyer | 4.2 | Not started
4.5 | 4 | 04 Sep | Property hunt | Suppliers | Tasting #2 — cumulative ≥8 SKUs scored; compute gross margin per SKU at quoted wholesale prices | Intern | 3.6 | Not started
4.6 | 4 | 04 Sep | Property hunt | Property | DECIDE the property (partners meeting, scorecard on screen) | Klaus+partners | 4.2,4.4 | Not started
4.7 | 4 | 04 Sep | Property hunt | Finance | Prepare bank-account opening docs; e-invoice + digital-signature applications ready to submit | Intern | 3.5 | Not started
WEEK 5 · Commit · Friday marker due 11 Sep — GATE WEEK
5.1 | 5 | 11 Sep | Commit | Property | SIGN LEASE at notary office; pay deposit against signed handover record (biên bản bàn giao) with meter readings + condition photos | Klaus+partners | 4.6 | Not started | GATE 1 — if not signed by Fri, trigger 5.7
5.2 | 5 | 11 Sep | Commit | Property | Site measurement + as-built sketch for designers | Intern | 5.1 | Not started
5.3 | 5 | 11 Sep | Commit | Build | Issue fit-out design brief to 3 contractors: one-way kitchen flow (raw→prep→cook→serve), 3-sink wash, grease trap, exhaust routing, walk-through window, 15–17 seats with outlets at every seat, counter layout | Klaus | 5.1 | Not started | Kitchen flow = what passes food-safety inspection
5.4 | 5 | 11 Sep | Commit | Finance | Open company bank account; partners contribute capital per founders' agreement schedule | Partners | 4.7 | Not started
5.5 | 5 | 11 Sep | Commit | Legal | Submit e-invoice + digital signature registrations | Intern | 4.7 | Not started
5.6 | 5 | 11 Sep | Commit | Ops | FALLBACK (only if lease not signed): convene same-day takeover-option meeting; activate best sang quán candidate from 2.5 | Klaus |  | Not started | Recovers 3–4 weeks of fit-out time
WEEK 6 · Build · Friday marker due 18 Sep
6.1 | 6 | 18 Sep | Build | Build | Compare 3 fit-out quotes line-by-line (AI-assisted comparison table); flag missing scope; select contractor | Klaus | 5.3 | Not started
6.2 | 6 | 18 Sep | Build | Build | Sign construction contract with milestone payments (30/50/20) and delay penalty clause | Klaus | 6.1 | Not started
6.3 | 6 | 18 Sep | Build | Build | Approve final drawings: kitchen flow, electrical load map, plumbing + grease trap spec, seating/outlet plan, facade + walk-through window | Klaus | 6.1 | Not started
6.4 | 6 | 18 Sep | Build | Legal | Ward police PCCC visit: get fire-safety category confirmed IN WRITING; buy extinguishers, exit signage, make internal fire rules file | Intern | 5.1 | Not started
6.5 | 6 | 18 Sep | Build | Build | Order long-lead equipment: espresso machine + grinder, display fridge, under-counter fridges, freezer, 2 commercial blenders | Intern | 6.1 | Not started | 2–6 week lead times — order before build starts
6.6 | 6 | 18 Sep | Build | Suppliers | Confirm 1 main + 2 backup suppliers; draft supply agreements: price validity 6 mo, lead times, return/expiry policy, VAT invoices | Intern | 4.5 | Not started
6.7 | 6 | 18 Sep | Build | Tech | Website LIVE: menu v1, map, opening-soon banner, email/Zalo capture | Software intern | 2.7 | Not started
6.8 | 6 | 18 Sep | Build | Build | Utilities: apply for commercial electricity (3-phase if needed), water, fibre internet install date | Intern | 5.1 | Not started
WEEK 7 · Build · Friday marker due 25 Sep
7.1 | 7 | 25 Sep | Build | Build | Construction kickoff; set site-meeting rhythm — intern on site 3×/week, photo update to Zalo group every 2 days | Intern | 6.2 | Not started
7.2 | 7 | 25 Sep | Build | Staff | Hire shift supervisor: partner-network referrals first, then job posts; Klaus interviews; offer letter + labor contract + SI registration | Klaus |  | Not started | Most important hire of the whole plan
7.3 | 7 | 25 Sep | Build | Staff | Book batch staff health certificates at district-level hospital (all hires incl. owner rep) | Intern |  | Not started | 100–300k VND/person; needed for food-safety dossier
7.4 | 7 | 25 Sep | Build | Legal | Build owner-certified food-safety training file: materials, attendance sheet, confirmation docs per Decree 155/2018 | Intern |  | Not started
7.5 | 7 | 25 Sep | Build | Legal | Assemble food safety dossier: application form, ERC copy, facility description + layout drawing, equipment list, staff list + health certs | Intern | 7.3,7.4 | Not started | Target 80% complete this week
7.6 | 7 | 25 Sep | Build | Marketing | Submit GrabFood + ShopeeFood merchant applications (ERC, bank account, menu photos required) | Klaus | 5.4 | Not started | Approval takes 1–3 weeks — start now
7.7 | 7 | 25 Sep | Build | Menu | Final pricing pass using ACTUAL supplier invoice prices; verify entry item ≤49k, blended COGS ≤34% | Klaus | 6.6 | Not started
WEEK 8 · Build · Friday marker due 02 Oct
8.1 | 8 | 02 Oct | Build | Staff | Recruit 4 staff (2 barista, 2 counter/kitchen): posts + referrals + paid trial shifts | Supervisor | 7.2 | Not started
8.2 | 8 | 02 Oct | Build | Staff | Labor contracts + social insurance registration for all staff (employer ~21.5%) | Intern | 8.1 | Not started | Use accountant/agency
8.3 | 8 | 02 Oct | Build | Suppliers | Compliance binder COMPLETE: tự công bố copy per resale SKU, spot-checked on the public portal; CO/CQ for any imports | Intern | 2.6 | Not started | Hard gate — no paper, no shelf
8.4 | 8 | 02 Oct | Build | Suppliers | Sign supplier price agreements (main + 2 backups); set weekly reorder day + emergency substitution protocol | Klaus | 6.6 | Not started
8.5 | 8 | 02 Oct | Build | Build | Mid-build inspection against BOQ; write snag list; hold milestone payment until cleared | Intern | 7.1 | Not started
8.6 | 8 | 02 Oct | Build | Brand | Product + space photography; menu board design + print order | Klaus | 6.7 | Not started
8.7 | 8 | 02 Oct | Build | Tech | Loyalty/pre-order app beta to 20 testers; collect feedback list | Software intern | 6.7 | Not started
WEEK 9 · Build · Friday marker due 09 Oct
9.1 | 9 | 09 Oct | Build | Build | Utilities live: 3-phase power energised, water, internet; log commercial electricity tariff | Intern | 6.8 | Not started
9.2 | 9 | 09 Oct | Build | Tech | POS installed + configured: full menu, modifiers, e-invoice integration, daily Z-report routine | Software intern | 5.5 | Not started
9.3 | 9 | 09 Oct | Build | Staff | Staff training week 1: recipes + blender SOPs, hygiene rules, POS drills, bilingual service scripts | Supervisor | 8.1 | Not started
9.4 | 9 | 09 Oct | Build | Ops | Write SOPs (AI-drafted, supervisor-verified): opening/closing checklists, cleaning schedule, fridge temperature log, waste log | Intern |  | Not started
9.5 | 9 | 09 Oct | Build | Marketing | Finalize opening campaign: content calendar, FB/IG accounts posting 3×/week warm-up, teaser posts in FB groups | Klaus |  | Not started
9.6 | 9 | 09 Oct | Build | Marketing | Partnership meetings ×5: Elite, Snap, F5, CrossFit Thao Dien, Body Shape / run clubs — pitch member discount + PT codes | Klaus |  | Not started
9.7 | 9 | 09 Oct | Build | Build | Checkpoint: build ≥70% complete vs schedule; if behind, invoke penalty clause + daily standups | Intern | 8.5 | Not started
WEEK 10 · Certify · Friday marker due 16 Oct — GATE WEEK
10.1 | 10 | 16 Oct | Certify | Build | Construction complete: deep clean, pest-control service contract signed, grease trap commissioned | Intern | 9.7 | Not started | GATE 2 week
10.2 | 10 | 16 Oct | Certify | Build | Equipment commissioning: espresso dial-in, blender test batches, fridge temps logged 48h continuously | Supervisor | 9.1 | Not started
10.3 | 10 | 16 Oct | Certify | Legal | SUBMIT food safety certificate application on HCMC portal + pay fee; record submission number + expected inspection window | Intern | 7.5,10.1 | Not started | THE opening gate — 15–20 working days
10.4 | 10 | 16 Oct | Certify | Menu | Menu LOCK: final recipes, portion specs (protein g on menu), allergen notes | Klaus | 7.7 | Not started
10.5 | 10 | 16 Oct | Certify | Finance | E-invoice live test: 10 test transactions end-to-end through cash register to tax portal | Intern | 9.2 | Not started
10.6 | 10 | 16 Oct | Certify | Marketing | Sign 3 partnership deals (gyms/run clubs): discount mechanics, PT commission codes, launch-event commitments | Klaus | 9.6 | Not started
WEEK 11 · Certify · Friday marker due 23 Oct
11.1 | 11 | 23 Oct | Certify | Legal | Mock food-safety audit against DFS inspection checklist; fix gaps; photo-document compliance state | Intern+Supervisor | 10.3 | Not started
11.2 | 11 | 23 Oct | Certify | Staff | Staff training week 2: full-menu timed run-throughs, food-safety drills, complaint handling, delivery-order flow | Supervisor | 9.3 | Not started
11.3 | 11 | 23 Oct | Certify | Marketing | Delivery menus uploaded with photos; delivery pricing set +15–20% over in-store | Klaus | 7.6 | Not started
11.4 | 11 | 23 Oct | Certify | Marketing | Soft-open guest list + invites: partners, run clubs, FB-group influentials, neighbours | Klaus |  | Not started
11.5 | 11 | 23 Oct | Certify | Suppliers | Initial inventory soft order (2 weeks of Base-case volume); receive + shelve + fridge plan | Intern | 8.4 | Not started
11.6 | 11 | 23 Oct | Certify | Tech | Loyalty QR live + printed table/counter materials | Software intern | 8.7 | Not started
11.7 | 11 | 23 Oct | Certify | Marketing | Outreach to 10 fitness micro-influencers: product-for-post offers for launch week | Klaus |  | Not started
WEEK 12 · Soft open · Friday marker due 30 Oct — GATE WEEK
12.1 | 12 | 30 Oct | Soft open | Legal | Host DFS INSPECTION: supervisor escorts, capture all feedback in writing | Intern | 10.3 | Not started | GATE 3 week
12.2 | 12 | 30 Oct | Soft open | Legal | Fix any inspection gaps within 48h; request re-check immediately | Intern | 12.1 | Not started | Never open uninspected
12.3 | 12 | 30 Oct | Soft open | Ops | Soft opening days 1–5: limited menu, friends/partners discount, feedback forms (paper + QR) | All | 11.2 | Not started | Target 300+ soft-open customers
12.4 | 12 | 30 Oct | Soft open | Ops | Daily ops debrief: ticket times, stockouts, till variance, staffing gaps — fix next morning | Supervisor | 12.3 | Not started
12.5 | 12 | 30 Oct | Soft open | Marketing | Run 2 community events: post-run shake mornings with partnered clubs | Klaus | 10.6 | Not started
12.6 | 12 | 30 Oct | Soft open | Tech | Live dashboard: covers/day, avg ticket, top sellers, channel mix (POS export) | Software intern | 9.2 | Not started
WEEK 13 · Soft open · Friday marker due 06 Nov
13.1 | 13 | 06 Nov | Soft open | Legal | Collect certificate; display in store; copy into compliance binder | Intern | 12.2 | Not started
13.2 | 13 | 06 Nov | Soft open | Ops | Full menu ON; GrabFood/ShopeeFood channels ON; monitor platform ratings daily | Supervisor | 12.3 | Not started
13.3 | 13 | 06 Nov | Soft open | Ops | Fix top-10 soft-open feedback items; retrain where patterns repeat | Supervisor | 12.4 | Not started
13.4 | 13 | 06 Nov | Soft open | Marketing | Announce grand-opening date everywhere; start small paid FB/IG budget boosting best organic posts | Klaus |  | Not started
13.5 | 13 | 06 Nov | Soft open | Marketing | Listings + press: Google Business Profile complete with photos, thaodien.app, expat guides | Klaus |  | Not started
13.6 | 13 | 06 Nov | Soft open | Suppliers | Calibrate stock from soft-open sell-through; confirm reorder rhythm with main supplier | Intern | 12.6 | Not started
WEEK 14 · Launch · Friday marker due 13 Nov — GATE WEEK
14.1 | 14 | 13 Nov | Launch | Ops | Grand-opening logistics: double staffing, promo stock, decorations, VCPMC music royalty settled | Intern | 13.1 | Not started | GATE 4 — target Sat opening
14.2 | 14 | 13 Nov | Launch | Marketing | Opening promos live: BOGO shakes, gym-member discount, first-100 free proffee | Klaus |  | Not started
14.3 | 14 | 13 Nov | Launch | Marketing | Influencer posts go live; founder post in Thao Dien FB group (story, not ad) | Klaus | 11.7 | Not started
14.4 | 14 | 13 Nov | Launch | Ops | Review push: QR cards at till, free-topping incentive — target ≥30 Google reviews ≥4.5★ | Supervisor |  | Not started
14.5 | 14 | 13 Nov | Launch | Tech | Measure launch: tx/day, ticket, channel mix, review velocity — daily to Zalo group | Software intern | 12.6 | Not started
14.6 | 14 | 13 Nov | Launch | Ops | Sunday-night debrief: what breaks under load, fix list for Monday | All |  | Not started
WEEK 15 · Stabilize · Friday marker due 20 Nov
15.1 | 15 | 20 Nov | Stabilize | Finance | Daily driver tracking vs P&L tab: tx/day, avg ticket, COGS%, delivery mix — variance flags at ±10% | Intern | 14.5 | Not started
15.2 | 15 | 20 Nov | Stabilize | Staff | Roster tuned to demand curve (validate gym-hours peak hypothesis: 6–9am, 5–8pm) | Supervisor |  | Not started
15.3 | 15 | 20 Nov | Stabilize | Suppliers | Lock reorder rhythm; start shrinkage/waste log review weekly | Intern |  | Not started
15.4 | 15 | 20 Nov | Stabilize | Ops | Weekly trading report v1 to Klaus + partners (sales, COGS%, top items, complaints, cash) | Intern | 15.1 | Not started
15.5 | 15 | 20 Nov | Stabilize | OEM | Send 3-month sales-velocity brief to Wana + Interfresh; request formulation meetings | Klaus |  | Not started | OEM phase opens here
WEEK 16 · Stabilize · Friday marker due 27 Nov
16.1 | 16 | 27 Nov | Stabilize | Finance | Month-1 close with accountant: VAT reconciliation, e-invoice audit, P&L actual vs budget | Intern | 15.1 | Not started
16.2 | 16 | 27 Nov | Stabilize | Ops | Customer survey n≥100 (QR at till + delivery inserts): NPS, menu gaps, price perception | Intern |  | Not started
16.3 | 16 | 27 Nov | Stabilize | OEM | University outreach: HCMUT / HUIT / Nong Lam food-tech faculties — project brief, stipend, IP assignment in internship agreement, Jan start | Klaus |  | Not started | Recruit 1–2 food-science interns
16.4 | 16 | 27 Nov | Stabilize | OEM | OEM decision meeting with partners: go/no-go + which SKUs, based on velocity data | Klaus+partners | 15.5 | Not started
16.5 | 16 | 27 Nov | Stabilize | Marketing | Q1 2027 marketing calendar — plan around Tet (mid-Feb 2027: closures, expat exodus, tourist peak) | Klaus |  | Not started
16.6 | 16 | 27 Nov | Stabilize | Ops | Retro: plan vs actual; update every blue assumption cell in this workbook with real numbers | All |  | Not started
RECURRING RITUALS
R.1 | — | ongoing | Recurring | Ops | EVERY FRIDAY: intern updates all statuses here + Milestones tab, sends 10-line report (moved / blocked / needs) | Intern |  | Not started | The heartbeat of the whole plan
R.2 | — | ongoing | Recurring | Ops | EVERY GATE MISS: same-day escalation to Klaus + fallback decision within 24h | Intern |  | Not started
R.3 | — | ongoing | Recurring | Build | DURING BUILD (W7–10): site photos to Zalo group every 2 days; weekly contractor meeting | Intern |  | Not started
R.4 | — | ongoing | Recurring | Finance | FROM SOFT OPEN: daily sales vs break-even tracking (85 tx/day Base) | Software intern |  | Not started
R.5 | — | ongoing | Recurring | Legal | MONTHLY: check Decree 15/2018 replacement status before any product declaration filing | Intern |  | Not started | Rules suspended Apr 2026 — will change
8.8 | 8 | 02 Oct | Build | Suppliers | NCC Whey A delayed delivery by 3 days; confirm new ETA, adjust stock plan, activate substitution protocol if needed | Intern | 8.4 | At risk | Delay of 3 days — assess soft-opening inventory impact and call backup supplier

## Suppliers
Supplier Long-List & Trial Scorecard
Goal: trial 5–10, pick 1 main + 2 backups by Week 8. HARD GATE per SKU: supplier's tự công bố (self-declaration) copy on file — no paper, no shelf. Score 1–5. Row 6 = worked example (edit it).
Supplier | Category | What to buy | Contact channel | Indicative price / MOQ | Tự công bố copy? | Taste /5 | Protein g | VND per g protein | Margin % /5 | Reliab. /5 | TOTAL | Notes / URL
Wana Beverage JSC | Local RTD + OEM path | Their existing protein shakes (coffee/choc/vanilla, 15–30g protein, can/PET); later OEM own label | inquiry@wana.com.vn · WhatsApp +84 365 135 789 · +84 28 7300 5789 | Mixed-SKU 20ft container for OEM; ask domestic small-lot wholesale | Ask | 4 | 25 |  | 4 | 4 |  | wanabeverage.com — closest local formulated RTD; best OEM bridge. Lead 25–30 days
Interfresh (Cu Chi) | OEM w/ ready formula | OEM protein milk 320ml (vanilla/straw/choc); free samples | info@interfresh.com.vn · WhatsApp +84 931 883 401 | MOQ ~1x20ft (~200 cartons); 25–35 days; shelf 18–24 mo | Ask | [6 empty] | interfresh.com.vn — ISO22000/HACCP; protein g/serving unpublished, ask
Vinamilk (via NPP) | Local RTD + inputs | Sure Prevent Gold 200ml; Greek yoghurt; fresh milk base | Territory distributor (NPP) — rep visits, order via Zalo | Retail ~32k/bottle; case discounts on volume | Ask |  | 8 |  |  |  |  | Clinical positioning, low protein/VND — good for older locals, weak for gym crowd
Nutifood (Värna) | Local RTD | Värna Complete 237ml lốc 6 ≈195k | Nutifood Eshop / Ngôi Nhà Dinh Dưỡng wholesale | ~32.5k/bottle retail | Ask | [6 empty] | Adult nutrition, not fitness — test demand before stocking deep
Abbott Ensure (3A) | Imported RTD (official) | Ensure RTD range | Abbott VN / 3A Nutrition distributor network | Abundant supply; ~13–20g protein/serving | Yes (official) | [6 empty] | Safe compliance, strong brand with locals; premium price
Gymstore dealer acct | Imported fitness (dealer) | ON whey, Barebells bars, Premier Protein RTD (30g) when stocked | 1800.2067 · service@gymstore.vn — ask 'chính sách đại lý' | Premier ~70k/bottle retail; dealer discount 10–25% | CHECK — parallel imports often lack VN declaration |  | 30 |  |  |  |  | Stock-outs common on imported RTD — reliability is the question
WheyShop dealer acct | Imported fitness (dealer) | Whey powders for in-house blends + bars | wheyshop.vn hotline/Zalo — dealer program | Dealer discounts 10–25% | CHECK | [6 empty] | On ON official retailer list
The Beast / Wheytot | Imported RTD | Applied Nutrition RTD shake 330/500ml | thebeast.vn · wheytot.com | 330ml ~80k retail; supply thin | CHECK |  | 25 |  |  |  |  | Frequent out-of-stock — backup only
Nutrition Depot VN | Imported (exclusive) | Their exclusively-distributed whey brands | nutritiondepot.vn | Wholesale on inquiry | Yes (importer) | [6 empty] | Note: their Thao Dien retail branch closed — negotiate hard
VINUT (Nam Viet) | Local OEM | 16g protein powder sticks (20/box, no added sugar); future RTD OEM | en.vinut.co/contact | Container-scale for OEM; sticks maybe smaller | Ask |  | 16 |  |  |  |  | Sticks could be retail shelf + travel product for tourists
Việt Úc JSC / Novaco | Bulk ingredient | WPC80 whey concentrate bulk for in-house blends | vietucjsc.com · novaco.vn | Bulk kg pricing — best margin path | Ask + lot papers | [6 empty] | In-house blends = 60–75% gross margin vs ~25–35% resale. Check import lot certificates
Kamereo | Fresh B2B platform | Chicken breast, eggs, produce, dairy — app ordering, VAT invoices | kamereo.vn app | Wholesale, next-day HCMC | n/a (fresh) | [6 empty] | One account for most fresh inputs; add Ba Huân (eggs), San Hà (poultry) direct as backups
Fill VND-per-g-protein manually from confirmed wholesale prices (e.g., Premier 70,000đ ÷ 30g ≈ 2,333đ/g; Sure Prevent 32,000đ ÷ 8g ≈ 4,000đ/g — lower is better). Compliance column: Yes / Copy on file / CHECK / No.